## PDCA Project Dashboard
PDCA Project Dashboard
Plan | Completion | Do | Completion
Analyze current bug resolution process | 100% | Implement the new bug categorization system | 100%
Brainstorm solutions for faster resolution | 80% | Test the new system on a pilot project | 90%
Select optimal solution for bug tracking | 100% | Gather feedback from developers and testers | 50%
Develop action plan for process changes | 100% | Action | 0%
Action | 0%
Action | 0%
Check | Completion | Act | Completion
Analyze bug resolution data post-implementation | 10% | Adjust categorization algorithm based on feedback | 6%
Evaluate whether resolution time meets targets | 0% | Update bug tracking documentation | 0%
Share results with stakeholders | 0% | Roll out system-wide implementation | 0%
|  | Train team on updated process | 0%
37%

## PDCA Project Template
PDCA Project
Fill in the non-shaded cells only. Data will populate in the shaded cells.
Project Name | Reduce Software Bug Resolution Time |  |  | Act | Plan
Process | Bug Tracking and Resolution Workflow |  |  | 1.5% | 63.33%
Team Leader |  |  |  | 3.333% | 60%
Cycle No. | 1 |  |  | Check | Do
Project Manager |  |  | Expected Hours | Progress | Updated
|  |  | 128 | 37.41% | MM/DD/YY
PDCA Stage | Actions | Responsible | Due Date | Duration (in hours) | Percent Complete | Status | Takeaways / Notes
Plan | Analyze current bug resolution process | Team | MM/DD/YY | 6 | 100% | Completed | Developers have varied interpretation of severity.
Plan | Brainstorm solutions for faster resolution | Team | MM/DD/YY | 8 | 80% | In Progress | Automating bug categorization can save time.
Plan | Select optimal solution for bug tracking | Team | MM/DD/YY | 4 | 100% | Completed | Implement automatic severity tagging in software.
Plan | Develop action plan for process changes | Lead Dev | MM/DD/YY | 4 | 100% | Completed | Clear ownership reduces confusion in execution.
Do | Implement the new bug categorization system | DevOps | MM/DD/YY | 24 | 100% | Completed | Initial hiccups in integration, but solved quickly.
Do | Test the new system on a pilot project | QA Team | MM/DD/YY | 12 | 90% | In Progress | QA feedback loops were slower than expected.
Do | Gather feedback from developers and testers | QA Lead | MM/DD/YY | 8 | 50% | In Progress | Mixed feedback; system needs minor adjustments.
Check | Analyze bug resolution data post-implementation | QA Lead | MM/DD/YY | 8 | 10% | In Progress
Check | Evaluate whether resolution time meets targets | Team | MM/DD/YY | 6 | 0% | Not Started
Check | Share results with stakeholders | Manager | MM/DD/YY | 2 | 0% | Not Started
Act | Adjust categorization algorithm based on feedback | Lead Dev | MM/DD/YY | 6 | 6% | In Progress
Act | Update bug tracking documentation | Team Lead | MM/DD/YY | 4 | 0% | Not Started
Act | Roll out system-wide implementation | IT Manager | MM/DD/YY | 24 | 0% | Not Started
Act | Train team on updated process | QA Lead | MM/DD/YY | 12 | 0% | Not Started
Plan | Action | Name | MM/DD/YY | 0 | 0% | Not Started
Plan | Action | Name | MM/DD/YY | 0 | 0% | Not Started
Do | Action | Name | MM/DD/YY | 0 | 0% | Not Started