## Stakeholder Analysis Template
Stakeholder Analysis
"The stakeholder analysis is an instrument to find out and present the needs of the different stakeholders of the respective company."
Stakeholder |  | Influence of Stakeholder [1;5] - [small;big] | Ability to Influence Stakeholders [1;5] - [small;big] | Attitude [1;5] - [pos;neg]
1. | Shareholder | 1 | 5 | 2
2. | Management | 2 | 1 | 2
3. | Labor Force | 3 | 2 | 3
4. | Customers | 4 | 3 | 3
5. | Supplier | 5 | 4 | 1
6. | Society | 1 | 5 | 1
7. | Bank - Money Provider | 2 | 1 | 4
8. | Government | 3 | 5 | 5
9. | Other | 4 | 2 | 5

## Action Plan
Stakeholder | Current Status | Desired Status | Gap Closure Strategy (Key Actions) | Owner | Success Metric
Shareholder | Supportive (4) | Advocate (5) | Quarterly ROI briefing; highlight waste reduction (Lean) impact on dividends. | Project Lead | Signed approval for Phase 2
Management | Resistant (2) | Supportive (4) | Direct 1-on-1 on cost-benefit; showcase pilot data to prove operational efficiency. | Project Sponsor | Full resource allocation for rollout
Labor Force | Resistant (2) | Neutral (3) | Hands-on training; "Gemba" walks to show how the new machine reduces physical strain. | Floor Manager | <10% negative feedback in survey
Customers | Neutral (3) | Supportive (4) | Marketing campaign on "Improved Quality Control"; launch loyalty pilot | Marketing Lead | >15% increase in repeat visits
Supplier | Resistant (2) | Neutral (3) | Review Service Level Agreements (SLAs); discuss long-term partnership benefits of JIT ordering. | Procurement | On-time delivery rate >95%
Society | Resistant (2) | Neutral (3) | Publish "Community Impact" report; highlight local sourcing and eco-friendly waste management. | PR Specialist | Positive local press coverage
Bank - Money Provider | Resistant (2) | Neutral (3) | Presentation of the Lean project’s risk mitigation; show "Current vs. Future State" cash flow projections. | CFO / Finance | Continued credit line stability
Government | Neutral (3) | Neutral (3) | Regular compliance audits; proactive reporting on sustainability metrics. | Legal/Compliance | Zero permit delays
Other
Note on B1: Continuous Quality Management: Advocate (5): Actively sticks their neck out for the project. Proactively influences others to join. Supportive (4): In favor of the change. Will provide resources and verbal support when asked. Neutral (3): Neither for nor against. Taking a "wait and see" approach; may be easily influenced. Resistant (2): Does not agree with the change but won't openly fight it. May slow-walk tasks. Blocker (1): Openly opposes the project. May actively work to undermine or block progress.
Note on C1: Continuous Quality Management: Advocate (5): Actively sticks their neck out for the project. Proactively influences others to join. Supportive (4): In favor of the change. Will provide resources and verbal support when asked. Neutral (3): Neither for nor against. Taking a "wait and see" approach; may be easily influenced. Resistant (2): Does not agree with the change but won't openly fight it. May slow-walk tasks. Blocker (1): Openly opposes the project. May actively work to undermine or block progress.

## Communication Plan
Target Audience | Key Message (The "WIIFM") | Channel / Method | Frequency
Shareholder | ROI and long-term value increase through Lean waste reduction. | Formal Executive Summary / Email | Monthly
Management | Operational stability and hitting KPIs without increasing overhead. | 1-on-1 Briefings / Dashboard | Bi-Weekly
Labor Force | "Easier, not harder." New tech reduces physical strain and errors. | Team Huddles / Visual Boards | Daily
Customers | Higher consistency and "Premium" experience coming to you. | In-store Signage / Social Media | Weekly
Supplier | Reliable, predictable ordering through JIT (Just-in-Time) delivery. | Procurement Portal / Call | Monthly
Society | We are a sustainable, eco-conscious community partner. | Press Release / Local Blog | Quarterly
Bank - Money Provider | Financial risk is being mitigated by data-driven process control. | Financial Performance Report | Quarterly
Government | We continue to improve yearly and are compliant with laws and regulations. | Audit | Yearly
Other